## Start Here
#VALUE!
Defects and Handover Checklist Template
BuilderForecast template - sample residential data included
Template purpose | Track defects, incomplete works, verification, client sign-off and handover document completion before practical completion.
Sample project | Lot 14 Riverside Estate - New 4 Bedroom Residence
Project address | 14 Rivergum Circuit, NSW
Template pricing | TBC - pricing to be set after review
Best suited for | Residential builders, owner-builders, project managers and small construction teams
Positioning note | BuilderForecast supports project budget control, variations, allowances, subcontractor costs, cost-to-complete and reporting. MeasureBuild is the separate estimating and drawing review service.
Current BuilderForecast templates page | https://builderforecast.online/templates
BuilderForecast website | https://builderforecast.online
MeasureBuild website | https://measurebuild.com.au/
Workbook contents
1 | Dashboard
2 | Defects Register
3 | Room Checklist
4 | Handover Pack
5 | Lists
How to use this template
1 | Update the status date and practical completion target on the Dashboard.
2 | Log every defect with location, priority, responsible trade and target closeout date.
3 | Use Room Checklist during pre-handover walks to avoid missed areas.
4 | Complete the Handover Pack checklist before client handover.
5 | Use final defect cost exposure in BuilderForecast cost-to-complete and reporting.

## Lists (hidden)
Dropdown Lists
Editable lists used by dropdowns across this workbook.
Priority | Status | Trade | YesNo
Low | Open | Builder | Yes
Medium | In Progress | Carpenter | No
High | Ready for Review | Painter | N/A
Critical | Closed | Plumber
| Deferred | Electrician
Tiler
Flooring
Cleaner
Joiner
Landscaper
Roofer
Cladding
Supplier

## Dashboard
#VALUE!
Defects and Handover Dashboard
Practical completion readiness, open defects and handover pack status.
Project | Lot 14 Riverside Estate - 4 bed residential | Status | Count
Address | 14 Rivergum Circuit, NSW | Open | 2
PM | A. Project Manager | In Progress | 1
Warranty Period Start | 2026-12-13 | Ready for Review | 1
Notes | Review weekly in final month and daily during handover week. | Closed | 1
Status Date | 2026-11-28 | Deferred | 1
Target Prac. Comp. | 2026-12-12
Client Walkthrough | 2026-12-05 | Total Defects | 6
Prepared For | Client / Owner | Open / In Progress | 3
Report Revision | Draft Rev A | High or Critical Open | 2
|  | Overdue Items | 1
|  | Closed Defects | 1
|  | Handover Docs Complete | 2 / 9

## Defects Register
Defects Register
Log, assign, close and verify defects before handover.
#VALUE!
Project | Lot 14 Riverside Estate - 4 bed residential
Address | 14 Rivergum Circuit, NSW
PM | A. Project Manager
Warranty Start | 2026-12-13
Defect ID | Date Raised | Area | Location | Category | Description | Priority | Trade Responsible | Status | Owner | Target Closeout | Completed Date | Verified By | Client Sign-off | Builder Sign-off | Cost Exposure | Days Open | Notes / Photo Ref
DEF-001 | 2026-11-20 | Kitchen | Island bench | Joinery | Minor chip to island end panel. | Medium | Joiner | Open | PM | 2026-11-28 |  |  | No | No | 450 | 8 | Photo DEF-001.jpg
DEF-002 | 2026-11-21 | Ensuite | Shower wall | Tiling | Uneven grout line at niche. | High | Tiler | In Progress | Site Supervisor | 2026-11-29 |  |  | No | No | 850 | 7 | Rework booked.
DEF-003 | 2026-11-22 | Bedroom 2 | North wall | Paint | Paint touch-up required around power point. | Low | Painter | Ready for Review | Site Supervisor | 2026-11-27 | 2026-11-26 | PM | No | Yes | 120 | 6 | Review at next walk.
DEF-004 | 2026-11-24 | External | Front entry | Cladding | Sealant missing at vertical cladding trim. | High | Cladding | Open | PM | 2026-11-30 |  |  | No | No | 650 | 4 | Weatherproofing item.
DEF-005 | 2026-11-25 | Bathroom | Vanity | Plumbing | Mixer handle loose. | Medium | Plumber | Closed | Site Supervisor | 2026-11-27 | 2026-11-27 | PM | Yes | Yes | 0 | 2 | Closed after plumber adjustment.
DEF-006 | 2026-11-26 | Garage | Floor | Concrete | Minor concrete spall near garage door. | Medium | Concrete | Deferred | Builder | 2026-12-08 |  |  | No | No | 500 | 2 | Agree repair method with client.

## Room Checklist
Room-by-Room Handover Checklist
Use during pre-handover inspection walks.
Project | Lot 14 Riverside Estate - 4 bed residential
Address | 14 Rivergum Circuit, NSW
PM | A. Project Manager
Warranty Start | 2026-12-13
Area / Room | Item | Check | Acceptable? | Defect ID | Responsible Trade | Due Date | Signed Off By | Status | Notes
Kitchen | Benchtops | No chips, scratches, stains or open joins. | No | DEF-001 | Joiner | 2026-11-28 |  | Open | Island end panel chip.
Kitchen | Cabinetry | Doors aligned, handles secure, drawers soft-close. | Yes |  | Joiner | 2026-11-28 | PM | Closed
Bathrooms | Waterproofed tiled areas | Tiles sound, grout clean, silicone complete. | No | DEF-002 | Tiler | 2026-11-29 |  | In Progress | Ensuite niche.
Bedrooms | Paint finish | Walls and trims clean with no visible patches. | No | DEF-003 | Painter | 2026-11-27 | PM | Ready for Review | Bedroom 2 touch-up.
External | Cladding and sealants | Flashings, trims and sealant lines complete. | No | DEF-004 | Cladding | 2026-11-30 |  | Open | Front entry trim.
Garage | Floor and door | Floor clean, door operates and seals. | No | DEF-006 | Concrete | 2026-12-08 |  | Deferred | Concrete spall.

## Handover Pack
Handover Pack Checklist
Documents, warranties, certificates, keys and final handover items.
Project | Lot 14 Riverside Estate - 4 bed residential
Address | 14 Rivergum Circuit, NSW
PM | A. Project Manager
Warranty Start | 2026-12-13
Item No | Handover Item | Required From | Due Date | Received Date | Responsible Person | Status | Notes
HO-001 | Occupation certificate / final approval | Certifier | 2026-12-10 |  | PM | Open | Required before handover.
HO-002 | Plumbing compliance certificate | Plumber | 2026-12-05 |  | Site Supervisor | Open
HO-003 | Electrical certificate and safety switch test | Electrician | 2026-12-05 |  | Site Supervisor | Open
HO-004 | Waterproofing certificates | Waterproofer | 2026-11-15 | 2026-11-12 | PM | Complete | Filed.
HO-005 | Appliance manuals and warranty cards | Appliance Supplier | 2026-12-01 |  | PM | Open
HO-006 | Paint colour schedule | Painter | 2026-11-25 | 2026-11-24 | PM | Complete | Add final touch-up tin labels.
HO-007 | Keys, remotes and access codes | Builder | 2026-12-08 |  | PM | Open | Prepare handover envelope.
HO-008 | Cleaning completion checklist | Cleaner | 2026-12-10 |  | Site Supervisor | Open
HO-009 | Defects closeout report | Builder | 2026-12-11 |  | PM | Open | Export from this workbook.