## Lists
Dropdown Lists
BuilderForecast ¦ Budget control tools for residential builders
Trade Category | Status | Confidence | Claim Status | Variation Status | Risk Score | Contract Type | Month
Preliminaries | Not Started | High | Entered | Draft | 1 - Low | Fixed Price | Jan
Consultants | On Track | Medium | Submitted | Pending | 2 - Mild | Cost Plus | Feb
Authority Fees & Contributions | Watch | Low | Approved | Approved | 3 - Moderate | Construction Management | Mar
Site Establishment | Over Budget | Unknown | Paid | Rejected | 4 - High | Owner-Builder | Apr
Demolition | Complete |  | Queried | Client Review | 5 - Very High | Pre-Contract | May
Earthworks | To Review |  | On Hold | Builder Review |  |  | Jun
In-Ground Services | At Risk | [5 empty] | Jul
Concrete | Closed | [5 empty] | Aug
Structural Framing | [6 empty] | Sep
Roofing | [6 empty] | Oct
Windows & External Doors | [6 empty] | Nov
External Cladding & Facade | [6 empty] | Dec
Internal Linings
Waterproofing
Joinery
Electrical
Hydraulic / Plumbing
Mechanical
Floor & Wall Finishes
Painting
External Works & Landscaping

## Start Here
BuilderForecast Project Budget Tracker
BuilderForecast ¦ Budget control tools for residential builders
Use this workbook to track a residential construction project budget, approved variations, actual costs, cost to complete, forecast final cost and contingency position. It is a management tool, not accounting or tax advice.
Project Setup | Enter Details | How to Use This Tracker
Project Name | Sample Residential Build | 1. Enter the original budget by trade in Budget Tracker.
Project Address |  | 2. Add invoices, subcontractor claims and paid costs in Actual Costs.
Client / Developer |  | 3. Record client, builder and trade variations in Variations. Only Approved variations flow to the budget.
Builder / Company |  | 4. Review Forecast Cost to Complete by trade every week or month.
Contract Type | Fixed Price | 5. Use the Dashboard to check revised budget, actuals, forecast final cost, variance and contingency.
Reporting Month | Jun | 6. Use the Contingency Calculator for a quick risk-based allowance check before pricing or committing.
GST Rate | 0.1
Starting Contingency Allowance | 35000 | Product Note
Prepared By |  | This template supports internal budget control and commercial review. Users should confirm contract, tax, insurance and accounting treatment with qualified advisers.
Last Updated | 2026-06-07

## Budget Tracker
Construction Budget Tracker
BuilderForecast ¦ Budget control tools for residential builders
Code | Cost Category | Original Budget | Approved Variations | Revised Budget | Actual Costs | Forecast Cost to Complete | Forecast Final Cost | Variance to Revised | % Spent | Status | Notes
01 | Preliminaries | 18000 | 0 | 18000 | 0 | 2500 | 2500 | 15500 | 0% | To Review
02 | Consultants | 12000 | 0 | 12000 | 0 | 1500 | 1500 | 10500 | 0% | To Review
03 | Authority Fees & Contributions | 9000 | 0 | 9000 | 0 | 0 | 0 | 9000 | 0% | To Review
04 | Site Establishment | 7500 | 0 | 7500 | 0 | 1000 | 1000 | 6500 | 0% | To Review
05 | Demolition | 5000 | 0 | 5000 | 0 | 0 | 0 | 5000 | 0% | To Review
06 | Earthworks | 22000 | 4620 | 26620 | 0 | 6000 | 6000 | 20620 | 0% | To Review
07 | In-Ground Services | 15000 | 0 | 15000 | 0 | 2500 | 2500 | 12500 | 0% | To Review
08 | Concrete | 55000 | 0 | 55000 | 24200 | 12000 | 36200 | 18800 | 44% | To Review
09 | Structural Framing | 68000 | 0 | 68000 | 19800 | 18000 | 37800 | 30200 | 29.12% | To Review
10 | Roofing | 36000 | 0 | 36000 | 9350 | 9000 | 18350 | 17650 | 25.97% | To Review
11 | Windows & External Doors | 42000 | 0 | 42000 | 0 | 8500 | 8500 | 33500 | 0% | To Review
12 | External Cladding & Facade | 33000 | 0 | 33000 | 0 | 7000 | 7000 | 26000 | 0% | To Review
13 | Internal Linings | 28000 | 0 | 28000 | 0 | 9000 | 9000 | 19000 | 0% | To Review
14 | Waterproofing | 8500 | 0 | 8500 | 0 | 2500 | 2500 | 6000 | 0% | To Review
15 | Joinery | 38000 | 0 | 38000 | 0 | 12000 | 12000 | 26000 | 0% | To Review
16 | Electrical | 26000 | 1045 | 27045 | 6050 | 7500 | 13550 | 13495 | 22.37% | To Review
17 | Hydraulic / Plumbing | 24000 | 0 | 24000 | 7150 | 6500 | 13650 | 10350 | 29.79% | To Review
18 | Mechanical | 6500 | 0 | 6500 | 0 | 1000 | 1000 | 5500 | 0% | To Review
19 | Floor & Wall Finishes | 32000 | 0 | 32000 | 0 | 9000 | 9000 | 23000 | 0% | To Review
20 | Painting | 18000 | 0 | 18000 | 0 | 4500 | 4500 | 13500 | 0% | To Review
21 | External Works & Landscaping | 28000 | 0 | 28000 | 0 | 9000 | 9000 | 19000 | 0% | To Review

## Actual Costs
Actual Costs, Claims and Invoices
BuilderForecast ¦ Budget control tools for residential builders
Date | Supplier / Subcontractor | Cost Category | Description | Invoice / Claim Ref | Claim Status | Amount ex GST | GST | Amount inc GST | Payment Due | Notes
2026-05-01 | ABC Concrete | Concrete | Slab claim 1 | INV-001 | Approved | 22000 | 2200 | 24200 | 2026-05-15 | Sample only
2026-05-07 | North Coast Roofing | Roofing | Roof materials deposit | INV-014 | Paid | 8500 | 850 | 9350 | 2026-05-21 | Sample only
2026-05-12 | FrameRight Carpentry | Structural Framing | Frame labour claim 1 | CLM-003 | Approved | 18000 | 1800 | 19800 | 2026-05-26 | Sample only
2026-05-18 | Bright Electrical | Electrical | Rough-in deposit | INV-044 | Submitted | 5500 | 550 | 6050 | 2026-06-01 | Sample only
2026-05-23 | PipeCo Plumbing | Hydraulic / Plumbing | Below ground plumbing | INV-021 | Approved | 6500 | 650 | 7150 | 2026-06-06 | Sample only
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0
[5 empty] | Entered | 0 | 0 | 0

## Variations
Variation Register
BuilderForecast ¦ Budget control tools for residential builders
Variation No. | Date | Cost Category | Description | Status | Raised By | Amount ex GST | GST | Amount inc GST | Approval Date | Notes
V001 | 2026-05-10 | Earthworks | Additional spoil removal | Approved | Builder | 4200 | 420 | 4620 | 2026-05-14 | Sample only
V002 | 2026-05-16 | Joinery | Upgrade vanity joinery | Pending | Client | 1800 | 180 | 1980 |  | Pending approval
V003 | 2026-05-24 | Electrical | Additional power points | Approved | Client | 950 | 95 | 1045 | 2026-05-28 | Sample only
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0
|  |  |  | Draft |  | 0 | 0 | 0

## Cost To Complete
Cost To Complete Review
BuilderForecast ¦ Budget control tools for residential builders
Code | Cost Category | Current Actual Costs | Committed / Known Costs | Forecast Remaining | Confidence | Key Risk / Assumption | Next Action | Review Date
01 | Preliminaries | 0 | 0 | 2500 | Medium |  |  | 2026-06-07
02 | Consultants | 0 | 0 | 1500 | Medium |  |  | 2026-06-07
03 | Authority Fees & Contributions | 0 | 0 | 0 | Medium |  |  | 2026-06-07
04 | Site Establishment | 0 | 0 | 1000 | Medium |  |  | 2026-06-07
05 | Demolition | 0 | 0 | 0 | Medium |  |  | 2026-06-07
06 | Earthworks | 0 | 0 | 6000 | Medium |  |  | 2026-06-07
07 | In-Ground Services | 0 | 0 | 2500 | Medium |  |  | 2026-06-07
08 | Concrete | 24200 | 0 | 12000 | Medium |  |  | 2026-06-07
09 | Structural Framing | 19800 | 0 | 18000 | Medium |  |  | 2026-06-07
10 | Roofing | 9350 | 0 | 9000 | Medium |  |  | 2026-06-07
11 | Windows & External Doors | 0 | 0 | 8500 | Medium |  |  | 2026-06-07
12 | External Cladding & Facade | 0 | 0 | 7000 | Medium |  |  | 2026-06-07
13 | Internal Linings | 0 | 0 | 9000 | Medium |  |  | 2026-06-07
14 | Waterproofing | 0 | 0 | 2500 | Medium |  |  | 2026-06-07
15 | Joinery | 0 | 0 | 12000 | Medium |  |  | 2026-06-07
16 | Electrical | 6050 | 0 | 7500 | Medium |  |  | 2026-06-07
17 | Hydraulic / Plumbing | 7150 | 0 | 6500 | Medium |  |  | 2026-06-07
18 | Mechanical | 0 | 0 | 1000 | Medium |  |  | 2026-06-07
19 | Floor & Wall Finishes | 0 | 0 | 9000 | Medium |  |  | 2026-06-07
20 | Painting | 0 | 0 | 4500 | Medium |  |  | 2026-06-07
21 | External Works & Landscaping | 0 | 0 | 9000 | Medium |  |  | 2026-06-07

## Contingency Calculator
Residential Build Contingency Calculator
BuilderForecast ¦ Budget control tools for residential builders
Use this as a quick internal risk check. It does not replace project-specific professional advice, contract review or detailed estimating.
Input | Selection / Value | Score | Scoring Guide
Project / Contract Value | 5665 |  | 1 | Low risk / known / confirmed
Project Stage | Pre-construction | 3 | 2 | Mild risk / mostly controlled
Drawing / Design Completion | Mostly complete | 2 | 3 | Moderate risk / needs monitoring
Trade Quote Coverage | Partial quotes received | 3 | 4 | High risk / incomplete information
Selections Status | Key selections outstanding | 4 | 5 | Very high risk / significant unknowns
Site Risk | Moderate | 3
Builder / Owner-Builder Experience | Experienced builder | 1 | BuilderForecast opinion
Use the calculator before locking the budget, then review contingency again after quotes, selections and site conditions become clearer. Most budget pain comes from unknown scope becoming real dollars later.
Output | Result | Formula
Total Risk Score | 16 | Sum of input scores
Recommended Contingency % | 15% | Tiered from score
Recommended Contingency $ | 849.75 | Project value x recommended %
Risk Rating | High | Low / Moderate / High / Extreme

## Dashboard
Project Budget Dashboard
BuilderForecast ¦ Budget control tools for residential builders
High-level view of the selected project budget, approved variations, actual costs, forecast final cost, variance and contingency position.
Project | Value | Commercial Read
Project Name | Sample Residential Build | Forecast within revised budget - keep monitoring cost to complete.
Contract Type | Fixed Price
Reporting Month | Jun | Metric | Result | Next Review Actions
Original Budget | 531500 | Budget Spend % | 12.39% | Update actual cost claims and invoices.
Approved Variations | 5665 | Variation % of Original Budget | 1.066% | Confirm pending variations and disputed scope.
Revised Budget | 537165 | Cost To Complete % | 24.01% | Review low-confidence cost-to-complete categories.
Actual Costs | 66550 | Categories Over Budget | 0 | Check whether contingency is still adequate.
Forecast Cost To Complete | 129000 | Approved Variation Count | 2 | Escalate over-budget categories before they become month-end surprises.
Forecast Final Cost | 195550 | Actual Cost Lines | 5
Forecast Variance | 341615
Starting Contingency | 35000
Forecast Contingency Remaining | 341615
Forecast Margin / Buffer % | 3452%

## Instructions
Quick Instructions
BuilderForecast ¦ Budget control tools for residential builders
This workbook is built for builders, owner-builders and residential project teams who want a clearer view of budget, actuals and forecast risk.
Step | What to Do | Why It Matters
1 | Complete Start Here with project details, GST rate and contingency allowance. | Sets the assumptions used across the workbook.
2 | Enter the original budget by trade category in Budget Tracker. | Creates the baseline for revised budget and variance reporting.
3 | Add actual invoices, claims and costs in Actual Costs. | Feeds actual cost totals back to each trade category.
4 | Record variations in the Variation Register. | Only approved variations are added to the revised budget.
5 | Review Cost To Complete regularly and update forecast remaining costs. | This is where the workbook becomes a forecasting tool, not just a cost dump.
6 | Use the Dashboard to identify over-budget trades and contingency pressure. | Shows the commercial position without digging through every tab.
7 | Use the Contingency Calculator when pricing or reviewing risk. | Gives a simple risk-based allowance check.
Important Customer Note
This template is a project management and commercial control tool. It does not replace accounting software, tax advice, legal advice, quantity surveying, contract administration advice or professional estimating.