## Start Here
Residential Construction Schedule Template
BuilderForecast template - sample residential data included
Template purpose | Plan and track residential build stages from pre-start through handover with baseline dates, actuals, completion percentage and a simple Gantt view.
Sample project | Lot 14 Riverside Estate - New 4 Bedroom Residence
Project address | 14 Rivergum Circuit, NSW
Template pricing | TBC - pricing to be set after review
Best suited for | Residential builders, owner-builders, project managers and small construction teams
Positioning note | BuilderForecast supports project budget control, variations, allowances, subcontractor costs, cost-to-complete and reporting. MeasureBuild is the separate estimating and drawing review service.
Current BuilderForecast templates page | https://builderforecast.online/templates
BuilderForecast website | https://builderforecast.online
MeasureBuild website | https://measurebuild.com.au/
Workbook contents
1 | Dashboard
2 | Construction Schedule
3 | Look Ahead
4 | Trade Contacts
5 | Lists
How to use this template
1 | Update the project start date and status date on the Dashboard.
2 | Review the Construction Schedule and edit planned start/finish dates to suit the project.
3 | Update actual dates and percentage complete during weekly site reviews.
4 | Use the Gantt view to identify trade sequencing and program pressure.
5 | Use Look Ahead to manage the next 2 to 4 weeks of blockers, inspections and procurement actions.

## Lists (hidden)
Dropdown Lists
Editable lists used by dropdowns across this workbook.
Status | Critical | Trade
Not Started | Yes | Preliminaries
In Progress | No | Surveyor
Complete |  | Earthworks
Delayed |  | Concrete
On Hold |  | Framing
Roofing
Windows
Cladding
Plumbing
Electrical
HVAC
Insulation
Plasterboard
Waterproofing
Tiling
Joinery
Painting
Flooring
Landscaping
Cleaning
Certifier

## Dashboard
Residential Construction Schedule Dashboard
Program snapshot, critical tasks and completion position.
Project | Lot 14 Riverside Estate - New 4 Bedroom Residence | Project Start | 2026-07-01
Address | 14 Rivergum Circuit, NSW | Status Date | 2026-07-15
PM | A. Project Manager | Target Practical Completion | 2026-12-12
Working Calendar | Monday to Friday, public holidays excluded by PM review | Revision | Baseline Rev A
Notes | Update weekly; link cost pressure back to BuilderForecast cost-to-complete. | Weather Allowance Days | 8
Total Tasks | 23 | Status | Count
Completed Tasks | 3 | Not Started | 18
In Progress | 2 | In Progress | 2
Delayed / On Hold | 0 | Complete | 3
Critical Open Tasks | 14 | Delayed | 0
Average % Complete | 16.74% | On Hold | 0

## Construction Schedule
Residential Construction Schedule
Baseline, actuals, status and simple week-by-week Gantt view.
[14 empty] | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-07-29 | 2026-08-05 | 2026-08-12 | 2026-08-19 | 2026-08-26 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-06 | 2026-10-13 | 2026-10-20 | 2026-10-27
WBS | Stage | Task | Trade / Owner | Planned Days | Planned Start | Planned Finish | Actual Start | Actual Finish | % Complete | Status | Variance Days | Critical? | Notes | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18
1.01 | Pre-start | Final drawing and specification review | PM | 5 | 2026-07-01 | 2026-07-05 | 2026-07-01 | 2026-07-05 | 100% | Complete | 0 | Yes | Confirm contract scope and allowances. | bar: 2026-07-01
1.02 | Pre-start | Site establishment and temporary fencing | Preliminaries | 3 | 2026-07-06 | 2026-07-08 | 2026-07-06 | 2026-07-08 | 100% | Complete | 0 | No | Site sign, amenities and safety setup. | bar: 2026-07-08
1.03 | Pre-start | Survey set-out | Surveyor | 2 | 2026-07-08 | 2026-07-09 | 2026-07-08 | 2026-07-09 | 100% | Complete | 0 | Yes | Set-out complete. | bar: 2026-07-08
2.01 | Base | Earthworks and excavation | Earthworks | 6 | 2026-07-10 | 2026-07-15 | 2026-07-10 |  | 75% | In Progress |  | Yes | Soft spot at garage under review. | bar: 2026-07-15
2.02 | Base | Underground services rough-in | Plumbing | 5 | 2026-07-14 | 2026-07-18 |  |  | 10% | In Progress |  | Yes | Coordinate with slab pour. | bar: 2026-07-15
2.03 | Base | Footings, piers and slab pour | Concrete | 9 | 2026-07-18 | 2026-07-26 |  |  | 0% | Not Started |  | Yes | Await pier approval. | bar: 2026-07-22
3.01 | Frame | Wall frame delivery and erection | Framing | 11 | 2026-07-29 | 2026-08-08 |  |  | 0% | Not Started |  | Yes | Frame order released. | bar: 2026-07-29 to 2026-08-05
3.02 | Frame | Roof trusses and bracing | Framing | 8 | 2026-08-05 | 2026-08-12 |  |  | 0% | Not Started |  | Yes | Dependent on frame inspection. | bar: 2026-08-05 to 2026-08-12
4.01 | Lock-up | Roofing and roof plumbing | Roofing | 12 | 2026-08-13 | 2026-08-24 |  |  | 0% | Not Started |  | Yes | Confirm roof blanket. | bar: 2026-08-19
4.02 | Lock-up | Windows and external doors | Windows | 8 | 2026-08-20 | 2026-08-27 |  |  | 0% | Not Started |  | Yes | Double glazing approved. | bar: 2026-08-26
4.03 | Lock-up | External cladding and flashings | Cladding | 15 | 2026-08-25 | 2026-09-08 |  |  | 0% | Not Started |  | Yes | Cladding substrate gap open. | bar: 2026-08-26 to 2026-09-02
5.01 | Rough-in | Plumbing rough-in | Plumbing | 11 | 2026-09-05 | 2026-09-15 |  |  | 0% | Not Started |  | No | bar: 2026-09-09
5.02 | Rough-in | Electrical rough-in | Electrical | 11 | 2026-09-05 | 2026-09-15 |  |  | 0% | Not Started |  | No | bar: 2026-09-09
5.03 | Rough-in | HVAC rough-in | HVAC | 8 | 2026-09-10 | 2026-09-17 |  |  | 0% | Not Started |  | No | bar: 2026-09-16
6.01 | Linings | Insulation and plasterboard | Plasterboard | 15 | 2026-09-18 | 2026-10-02 |  |  | 0% | Not Started |  | Yes | bar: 2026-09-23 to 2026-09-30
6.02 | Wet Areas | Waterproofing | Waterproofing | 6 | 2026-10-03 | 2026-10-08 |  |  | 0% | Not Started |  | Yes | Inspection required.
6.03 | Wet Areas | Wall and floor tiling | Tiling | 16 | 2026-10-09 | 2026-10-24 |  |  | 0% | Not Started |  | Yes | Tile selections due.
7.01 | Fixing | Joinery install | Joinery | 14 | 2026-10-21 | 2026-11-03 |  |  | 0% | Not Started |  | Yes
7.02 | Fixing | Internal doors, skirting and architraves | Framing | 11 | 2026-10-28 | 2026-11-07 |  |  | 0% | Not Started |  | No
7.03 | Finishes | Painting | Painting | 15 | 2026-11-04 | 2026-11-18 |  |  | 0% | Not Started |  | No
7.04 | Finishes | Flooring install | Flooring | 9 | 2026-11-17 | 2026-11-25 |  |  | 0% | Not Started |  | No
8.01 | Completion | Final fit-off and commissioning | Plumbing | 11 | 2026-11-23 | 2026-12-03 |  |  | 0% | Not Started |  | Yes | Coordinate electrical and plumbing.
8.02 | Completion | Defects, clean and handover pack | PM | 9 | 2026-12-04 | 2026-12-12 |  |  | 0% | Not Started |  | Yes | Use defects template.

## Look Ahead
2-4 Week Look Ahead
Short-term site actions, blockers and inspection readiness.
Week | Date | Trade | Action / Task | Dependency | Inspection / Hold Point | Owner | Due Date | Status | Notes
Week 1 | 2026-07-15 | Concrete | Confirm pier inspection and slab pour booking. | Engineer inspection | Pier / footing inspection | Site Supervisor | 2026-07-18 | Open | Concrete booking depends on approval.
Week 1 | 2026-07-16 | Plumbing | Complete under-slab rough-in. | Trench inspection | Plumbing inspection | Plumber | 2026-07-18 | Open | Coordinate with concrete.
Week 2 | 2026-07-22 | Framing | Confirm wall frame delivery date. | Slab cure / survey check | Frame delivery QA | PM | 2026-07-25 | Open
Week 3 | 2026-07-29 | Roofing | Confirm roof sheet colour and roof blanket. | Truss completion | Roof safety plan | PM | 2026-08-05 | Open | Selections dependency.

## Trade Contacts
Trade Contacts
Trade contacts and lead-time notes.
Trade | Company | Contact | Phone | Email | Notice Required | Contract Value | Notes
Concrete | Northside Concrete Pty Ltd | Dan Morris | 02 8000 1111 | dan@example.com | 7 days | 86515 | Award pending RFI closeout.
Framing | Riverside Frames | Kate Wong | 02 8000 2222 | kate@example.com | 14 days | 62400 | Frame order released after slab pour.
Roofing | TrueLine Roofing | Sam Patel | 02 8000 3333 | sam@example.com | 10 days | 38500 | Confirm blanket and flashings.
Cladding | Facade Works NSW | Olivia Chen | 02 8000 4444 | olivia@example.com | 14 days | 44200 | Substrate scope unresolved.