## Start Here
Selections Schedule Template
BuilderForecast template - sample residential data included
Template purpose | Manage client selections, allowances, approval status, ordering dates, delivery ETA and budget variance.
Sample project | Lot 14 Riverside Estate - New 4 Bedroom Residence
Project address | 14 Rivergum Circuit, NSW
Template pricing | TBC - pricing to be set after review
Best suited for | Residential builders, owner-builders, project managers and small construction teams
Positioning note | BuilderForecast supports project budget control, variations, allowances, subcontractor costs, cost-to-complete and reporting. MeasureBuild is the separate estimating and drawing review service.
Current BuilderForecast templates page | https://builderforecast.online/templates
BuilderForecast website | https://builderforecast.online
MeasureBuild website | https://measurebuild.com.au/
Workbook contents
1 | Dashboard
2 | Selections Schedule
3 | Supplier Contacts
4 | Lists
How to use this template
1 | Update the project, contract allowance and status date on the Dashboard.
2 | Enter each required selection with allowance, actual price and decision deadline.
3 | Use status fields to track Required, Selected, Approved, Ordered and Delivered items.
4 | Monitor variance to allowance and overdue selections before they affect procurement or program.
5 | Approved actual costs can be reflected in BuilderForecast allowances and cost-to-complete.

## Lists (hidden)
Dropdown Lists
Editable lists used by dropdowns across this workbook.
Status | Ordered | Owner | Category
Required | No | Client | Appliances
Selected | Yes | Builder | Tapware
Approved | Partial | PM | Sanitaryware
Ordered |  | Interior Designer | Tiles
Delivered |  | Supplier | Flooring
Installed |  |  | Paint
On Hold |  |  | Cabinetry
Lighting
Hardware
External Finishes

## Dashboard
Selections Dashboard
Client selections, allowance variance and procurement risk snapshot.
Project | Lot 14 Riverside Estate - New 4 Bedroom Residence | Status Date | 2026-07-15
Address | 14 Rivergum Circuit, NSW | Selections Manager | A. Project Manager
Client | Riverside Owners | GST / Allowance Basis | Inc GST
Notes | Use this with allowance tracking and cost-to-complete review. | Next Client Meeting | 2026-07-22
Total Selections | 8 | Status | Count
Approved / Ordered | 4 | Required | 2
Overdue Decisions | 1 | Selected | 2
Total Allowance | 34850 | Approved | 4
Total Actual | 36405 | Ordered | 0
Variance to Allowance | 1555 | Delivered | 0
|  | Installed | 0
|  | On Hold | 0

## Selections Schedule
Selections Schedule
Track selections, approvals, orders, delivery and allowance variance.
Selection ID | Area / Room | Category | Item | Supplier | Product / Model | Colour / Finish | Allowance Inc GST | Actual Inc GST | Variance | Required By | Decision Status | Ordered? | Order Date | Delivery ETA | Lead Time Days | Owner | Risk / Notes
SEL-001 | Kitchen | Appliances | Oven and cooktop package | Winning Appliances | Bosch 600mm electric package | Stainless steel | 4200 | 4650 | 450 | 2026-07-20 | Approved | Yes | 2026-07-13 | 2026-08-05 | 23 | Client | Within lead time.
SEL-002 | Kitchen | Cabinetry | Kitchen cabinetry finish | JoineryPro | Polytec laminate doors | Oyster Grey matt | 7800 | 8200 | 400 | 2026-07-18 | Approved | No |  |  |  | Client | Confirm handle profile.
SEL-003 | Bathrooms | Tiles | Main bathroom wall tile | Tile Warehouse | 300x600 porcelain wall tile | Warm white satin | 3500 | 3925 | 425 | 2026-07-16 | Selected | No |  |  |  | Client | Approval needed this week.
SEL-004 | Ensuite | Tapware | Tapware package | Reece | Milli Pure shower mixer and rail | Brushed nickel | 2400 | 3150 | 750 | 2026-07-15 | Required | No |  |  |  | Client | Potential allowance overrun.
SEL-005 | Whole house | Flooring | Engineered timber flooring | Flooring Direct | Oak engineered board | Natural oak | 11800 | 11250 | -550 | 2026-08-01 | Approved | Yes | 2026-07-12 | 2026-08-18 | 37 | Builder | Lead time confirmed.
SEL-006 | External | Paint | External paint colours | Dulux | Weathershield system | Monument / Surfmist | 2500 | 2500 | 0 | 2026-08-05 | Selected | No |  |  |  | Interior Designer | Awaiting client sign-off.
SEL-007 | Laundry | Sanitaryware | Laundry trough and mixer | Reece | Everhard 45L trough | Chrome | 850 | 780 | -70 | 2026-07-25 | Approved | No |  |  |  | PM | Under allowance.
SEL-008 | Bedrooms | Hardware | Door furniture package | Bunnings Trade | Lockwood Velocity set | Satin chrome | 1800 | 1950 | 150 | 2026-08-08 | Required | No |  |  |  | Client | Confirm privacy sets.

## Supplier Contacts
Supplier Contacts
Selection supplier contacts and ordering notes.
Supplier | Category | Contact | Phone | Email | Lead Time | Account Ref | Notes
Winning Appliances | Appliances | Sarah Lee | 02 9000 1111 | sarah@example.com | 3-4 weeks | TRADE-0041 | Confirm delivery booking 7 days prior.
Reece | Tapware / Sanitaryware | Trade Counter | 02 9000 2222 | trade@example.com | 2-5 weeks | REECE-221 | Check brushed nickel stock.
Tile Warehouse | Tiles | Marco Silva | 02 9000 3333 | marco@example.com | 4-6 weeks | TILE-118 | Order attic stock with tile package.
Flooring Direct | Flooring | Amelia Tan | 02 9000 4444 | amelia@example.com | 5 weeks | FLOOR-771 | Moisture reading required before install.