## Start Here
Trade Quote Comparison Template
BuilderForecast template - sample residential data included
Template purpose | Compare residential trade quotes side by side, check scope exclusions, score commercial risk and document quote clarifications before awarding work.
Sample project | Lot 14 Riverside Estate - New 4 Bedroom Residence
Project address | 14 Rivergum Circuit, NSW
Template pricing | TBC - pricing to be set after review
Best suited for | Residential builders, owner-builders, project managers and small construction teams
Positioning note | BuilderForecast supports project budget control, variations, allowances, subcontractor costs, cost-to-complete and reporting. MeasureBuild is the separate estimating and drawing review service.
Current BuilderForecast templates page | https://builderforecast.online/templates
BuilderForecast website | https://builderforecast.online
MeasureBuild website | https://measurebuild.com.au/
Workbook contents
1 | Quote Dashboard
2 | Quote Comparison
3 | Scope Checklist
4 | Clarifications & RFIs
5 | Lists
How to use this template
1 | Update the project information and budget allowance on the Quote Dashboard.
2 | Enter each tenderer quote in Quote Comparison. Yellow/input cells are intended for editing.
3 | Use the weighted score as a decision support tool, not as the only award decision.
4 | Review Scope Checklist and Clarifications before issuing a recommendation or purchase order.
5 | Move final budget, awarded amount and scope risk into BuilderForecast once the trade is awarded.

## Lists
Dropdown Lists
Editable lists used by dropdowns across this workbook.
Risk Rating | Recommendation | GST Status | Included | Status
Low | Recommended | Ex GST | Yes | Open
Medium | Shortlist | Inc GST | No | Sent to tenderer
High | Clarify | No GST | Clarify | Answered
| Decline |  | N/A | Closed

## Quote Dashboard
Trade Quote Comparison Dashboard
Residential tender comparison - budget, quote risk and recommendation snapshot.
Project | Lot 14 Riverside Estate - New 4 Bedroom Residence | Trade Package | Concrete slab and external hardstands
Address | 14 Rivergum Circuit, NSW | Budget Allowance Ex GST | 82000
Status Date | 2026-07-15 | GST Rate | 10%
Estimator / PM | A. Project Manager | Decision Required By | 2026-07-25
Lowest Quote Inc GST | 81620 | Quote Summary | Total Inc GST | Variance to Budget | Weighted Score | Rank
Recommended Tenderer | Precision Residential Concrete | Northside Concrete Pty Ltd | 86515 | -3685 | 90 | 2
Budget Variance Inc GST | -550 | Rivergum Slabs & Civil | 81620 | -8580 | 79 | 4
Open Clarifications | 2 | Precision Residential Concrete | 89650 | -550 | 92 | 1
|  | Metro Formwork & Concrete | 87868 | -2332 | 81 | 3

## Quote Comparison
Trade Quote Comparison
Pre-filled sample: concrete slab and external hardstands tender comparison.
Tenderer | ABN / Ref | Quote Date | Quote Ex GST | GST | Total Inc GST | GST Status | Lead Time Days | Program Notes | Variance to Budget | Variance % | Price Score | Scope Score | Program Score | Commercial Score | Risk Rating | Weighted Score | Rank | Recommendation
Northside Concrete Pty Ltd | ABN 11 222 333 444 | 2026-07-03 | 78650 | 7865 | 86515 | Ex GST | 18 | Can start after pier inspection. Pump included. | -3685 | -4.085% | 94 | 88 | 84 | 90 | Low | 90 | 2 | Shortlist
Rivergum Slabs & Civil | ABN 55 666 777 888 | 2026-07-05 | 74200 | 7420 | 81620 | Ex GST | 24 | Lower price; excludes pump and termite barrier. | -8580 | -9.512% | 100 | 72 | 76 | 74 | Medium | 79 | 4 | Shortlist
Precision Residential Concrete | ABN 99 111 222 333 | 2026-07-06 | 81500 | 8150 | 89650 | Ex GST | 16 | Strong scope coverage and fastest start. | -550 | -0.6098% | 91 | 94 | 92 | 88 | Low | 92 | 1 | Recommended
Metro Formwork & Concrete | ABN 44 555 666 777 | 2026-07-07 | 79880 | 7988 | 87868 | Ex GST | 21 | Includes mesh, set-downs and basic saw cuts. | -2332 | -2.585% | 93 | 82 | 80 | 82 | Medium | 81 | 3 | Shortlist

## Scope Checklist
Quote Scope Checklist
Use before awarding a trade to identify missing inclusions, exclusions and clarification items.
Ref | Scope Item | Expected in Quote | Tenderer Response | Included? | Risk | Cost Exposure Inc GST | Clarification Required | Owner | Notes
C-01 | Site set-out and levels | Gridlines, slab RL, set-downs and datum confirmed | Included in Northside quote | Yes | Low | 0 | None | PM | Confirm final set-out before start
C-02 | Excavation and spoil | Allowance for minor trimming and spoil removal | Excludes rock excavation | Clarify | Medium | 3500 | Confirm spoil allowance and rock rates | Estimator | Request unit rates
C-03 | Termite barrier coordination | Coordination with termite contractor and penetrations | Excluded by Rivergum | No | High | 4200 | Confirm whether supply and installation included | PM | Potential budget gap
C-04 | Concrete pump | Pump included where truck access limited | Excluded by Rivergum | Clarify | Medium | 2800 | Confirm pump allowance | Estimator | Likely required for rear slab pour
C-05 | Mesh and reinforcement placement | Mesh, ligatures, chairs and cover blocks | Included | Yes | Low | 0 | None | Site Supervisor | Check engineering revision
C-06 | Saw cuts and curing | Saw cuts, curing compound and protection | Included by 2 tenderers only | Clarify | Medium | 1200 | Confirm curing and saw cut scope | PM | Quality risk if missed

## Clarifications & RFIs
Clarifications & RFIs
Track tender clarifications before award.
RFI No | Date Raised | Tenderer | Question / Clarification | Owner | Due Date | Response Summary | Status | Decision Impact
RFI-QC-001 | 2026-07-08 | Rivergum Slabs & Civil | Confirm whether pump, termite barrier coordination and saw cuts are included. | Estimator | 2026-07-12 | Pending response | Open | Could change lowest quote ranking
RFI-QC-002 | 2026-07-08 | Northside Concrete Pty Ltd | Confirm rock excavation exclusion and unit rate per m3. | PM | 2026-07-13 | Unit rate provided at $180/m3 plus disposal. | Answered | Add risk allowance if rock likely
RFI-QC-003 | 2026-07-09 | All tenderers | Confirm latest engineering revision S03 Rev C used. | PM | 2026-07-12 | 2 of 4 confirmed | Open | Do not award until confirmed