## Start Here
Residential Scope Gap Checklist Pack
BuilderForecast template - sample residential data included
Template purpose | Identify quote and scope gaps before award across concrete, framing, roofing and cladding packages.
Sample project | Lot 14 Riverside Estate - New 4 Bedroom Residence
Project address | 14 Rivergum Circuit, NSW
Template pricing | TBC - pricing to be set after review
Best suited for | Residential builders, owner-builders, project managers and small construction teams
Positioning note | BuilderForecast supports project budget control, variations, allowances, subcontractor costs, cost-to-complete and reporting. MeasureBuild is the separate estimating and drawing review service.
Current BuilderForecast templates page | https://builderforecast.online/templates
BuilderForecast website | https://builderforecast.online
MeasureBuild website | https://measurebuild.com.au/
Workbook contents
1 | Summary
2 | Concrete
3 | Framing
4 | Roofing
5 | Cladding
6 | Lists
How to use this template
1 | Use each trade checklist when reviewing quotes, scopes, drawings and exclusions.
2 | Mark Included as Yes, No, Clarify or N/A.
3 | Enter likely exposure where a missing item could affect the budget.
4 | Review the Summary tab to prioritise high-risk gaps and open actions.
5 | Use the checklist alongside BuilderForecast to manage scope risk and protect contingency.

## Lists
Dropdown Lists
Editable lists used by dropdowns across this workbook.
Included | Risk | Status | Owner
Yes | Low | Open | PM
No | Medium | Clarifying | Estimator
Clarify | High | Resolved | Site Supervisor
N/A |  | Closed | Builder
Client
Architect
Engineer

## Summary
Scope Gap Summary
Review gap count, high-risk items and potential budget exposure by trade.
Project | Lot 14 Riverside Estate - New 4 Bedroom Residence
Address | 14 Rivergum Circuit, NSW
Status Date | 2026-07-15
Use Case | Tender/quote review before award and budget upload.
Trade | Checklist Items | Scope Gaps | High Risk Gaps | Potential Exposure | Open Actions
Concrete | 8 | 5 | 2 | 13800 | 5
Framing | 7 | 4 | 2 | 12500 | 4
Roofing | 6 | 4 | 3 | 15200 | 4
Cladding | 6 | 4 | 3 | 18600 | 4
|  | Total Potential Exposure |  | 60100

## Concrete
Concrete Scope Gap Checklist
Pre-filled residential scope review checklist. Edit rows to suit the project and tender scope.
Ref | Area | Checklist Item | What to Confirm | Included? | Risk | Potential Cost Exposure | Action Required | Owner | Due Date | Status | Notes | Gap Flag
CON-01 | Preliminaries | Latest structural drawings used | Confirm engineer revision, slab set-downs, pier notes and footing details are priced. | Clarify | High | 2500 | Confirm drawings S01-S05 Rev C used by trade. | Estimator | 2026-07-20 | Open | High risk if older engineering used. | Scope Gap
CON-02 | Earthworks | Bulk excavation and trimming | Confirm who trims to underside of slab, removes spoil and manages unsuitable material. | Clarify | Medium | 3500 | Request excavation exclusions and rock rates. | PM | 2026-07-20 | Open | Rock and spoil often become variation items. | Scope Gap
CON-03 | Footings / piers | Bored piers and deepened edge beams | Confirm bored pier quantity, depth assumptions, cages and concrete strength. | Yes | Medium | 0 | Check against engineer schedule. | Estimator | 2026-07-20 | Resolved | Included in preferred quote. | OK
CON-04 | Slab | Vapour barrier, mesh, chairs, set-downs | Confirm vapour barrier, reinforcement chairs, wet area set-downs and penetrations. | Yes | Low | 0 | Verify against architectural wet area layout. | Site Supervisor | 2026-07-20 | Resolved |  | OK
CON-05 | Termite system | Termite barrier coordination | Confirm termite treatment scope and penetration collars are included or by others. | No | High | 4200 | Allocate termite scope to trade or separate supplier. | PM | 2026-07-20 | Open | Budget exposure if missed. | Scope Gap
CON-06 | Concrete pump | Pump and line requirements | Confirm pump included for restricted access and rear pours. | Clarify | Medium | 2800 | Add pump allowance or confirm access. | Estimator | 2026-07-20 | Open |  | Scope Gap
CON-07 | Finishes | Garage broom finish and patio finish | Confirm trowel, broom or exposed finish and curing requirements. | Yes | Low | 0 | Confirm finish spec in quote. | PM | 2026-07-20 | Closed |  | OK
CON-08 | Waste / clean-up | Concrete waste and slurry control | Confirm washout, slurry control and clean-up included. | Clarify | Low | 800 | Clarify environmental controls. | Site Supervisor | 2026-07-20 | Open |  | Scope Gap

## Framing
Framing Scope Gap Checklist
Pre-filled residential scope review checklist. Edit rows to suit the project and tender scope.
Ref | Area | Checklist Item | What to Confirm | Included? | Risk | Potential Cost Exposure | Action Required | Owner | Due Date | Status | Notes | Gap Flag
FRM-01 | Drawings | Latest structural and truss layouts | Confirm frame trade has architectural, engineering and truss setout revisions. | Clarify | High | 3000 | Issue drawing register with latest revisions. | PM | 2026-07-20 | Open | Avoid rework from outdated plans. | Scope Gap
FRM-02 | Timber / steel frame | Supply and installation split | Confirm whether quote is supply/install or install-only and who orders materials. | Yes | High | 0 | Confirm purchasing responsibility. | Estimator | 2026-07-20 | Resolved |  | OK
FRM-03 | Lintels / beams | LVL, steel beams and posts | Confirm engineering beams, brackets, hold-downs and connectors included. | Clarify | High | 6500 | Request beam schedule inclusions. | Estimator | 2026-07-20 | Open | Common high exposure gap. | Scope Gap
FRM-04 | Bracing | Wall bracing and tie-down | Confirm bracing panels, straps, tie-down rods and inspection coordination. | Yes | Medium | 0 | Review bracing plan. | Site Supervisor | 2026-07-20 | Resolved |  | OK
FRM-05 | Carpentry set-outs | Wet area and recessed niches | Confirm set-downs, noggings, wall niches, shower screens and accessories blocking. | Clarify | Medium | 1800 | Confirm internal fit-off backing requirements. | PM | 2026-07-20 | Open | Avoid later fix-out variations. | Scope Gap
FRM-06 | External openings | Window and door openings | Confirm openings include flashings support, sill details and tolerances. | Yes | Medium | 0 | Cross-check window schedule. | Estimator | 2026-07-20 | Resolved |  | OK
FRM-07 | Temporary bracing | Temporary works during erection | Confirm temporary bracing, safety and weather protection included. | Clarify | Low | 1200 | Clarify temporary works. | Site Supervisor | 2026-07-20 | Open |  | Scope Gap

## Roofing
Roofing Scope Gap Checklist
Pre-filled residential scope review checklist. Edit rows to suit the project and tender scope.
Ref | Area | Checklist Item | What to Confirm | Included? | Risk | Potential Cost Exposure | Action Required | Owner | Due Date | Status | Notes | Gap Flag
ROF-01 | Roof material | Roof sheet / tile specification | Confirm profile, colour, gauge and supplier lead time. | Yes | Medium | 0 | Attach colour schedule to quote. | PM | 2026-07-20 | Resolved |  | OK
ROF-02 | Roof plumbing | Gutters, fascia and downpipes | Confirm gutters, downpipes, rainheads, sumps, overflows and fascia scope. | Clarify | High | 5200 | Request itemised roof plumbing inclusions. | Estimator | 2026-07-20 | Open | Can be missed when roofing and plumbing are split. | Scope Gap
ROF-03 | Flashings | Apron, barge, valley and wall flashings | Confirm all flashings to penetrations, parapets and cladding interfaces. | Clarify | High | 4800 | Confirm interface responsibilities with cladding trade. | PM | 2026-07-20 | Open | High leak risk if unclear. | Scope Gap
ROF-04 | Sarking / insulation | Sarking, blanket and roof insulation | Confirm whether roof blanket and foil are included and rating matches spec. | No | High | 3600 | Assign insulation scope to roofing or separate trade. | Estimator | 2026-07-20 | Open | Budget and energy compliance gap. | Scope Gap
ROF-05 | Penetrations | Vents, flues and solar provisions | Confirm flashings for vents, exhausts, flues and future solar penetrations. | Clarify | Medium | 1600 | Coordinate with services trades. | Site Supervisor | 2026-07-20 | Open |  | Scope Gap
ROF-06 | Access and safety | Edge protection and roof access | Confirm edge protection, harness points and access requirements included. | Yes | Medium | 0 | Check WHS responsibility. | PM | 2026-07-20 | Resolved |  | OK

## Cladding
Cladding Scope Gap Checklist
Pre-filled residential scope review checklist. Edit rows to suit the project and tender scope.
Ref | Area | Checklist Item | What to Confirm | Included? | Risk | Potential Cost Exposure | Action Required | Owner | Due Date | Status | Notes | Gap Flag
CLD-01 | Cladding material | Cladding type and profile | Confirm fibre cement profile, thickness, orientation, colour and finish system. | Yes | Medium | 0 | Attach facade schedule. | PM | 2026-07-20 | Resolved |  | OK
CLD-02 | Moisture management | Wrap, cavity battens and vapour-permeable membrane | Confirm membrane, cavity system, battens and drainage are included. | Clarify | High | 5400 | Request wall build-up inclusions. | Estimator | 2026-07-20 | Open | High weatherproofing risk. | Scope Gap
CLD-03 | Flashings / trims | Corners, sills, parapets and junction trims | Confirm all proprietary trims and flashings are included and who supplies them. | Clarify | High | 4200 | Coordinate with roofing and window trades. | PM | 2026-07-20 | Open | Interface risk. | Scope Gap
CLD-04 | Substrate | Plywood, battens and fixing substrate | Confirm substrate responsibility and fixing centres. | No | High | 6800 | Assign substrate scope before award. | Estimator | 2026-07-20 | Open | Could become major variation. | Scope Gap
CLD-05 | Painting / coating | Factory finish vs site painting | Confirm whether cladding coating is factory-applied or painter scope. | Clarify | Medium | 2200 | Clarify paint responsibility. | PM | 2026-07-20 | Open |  | Scope Gap
CLD-06 | Waste and offcuts | Waste allowance and protection | Confirm waste factor and protection to finished surfaces included. | Yes | Low | 0 | Check quote inclusions. | Site Supervisor | 2026-07-20 | Closed |  | OK