## Start Here
Variation Register Template
BuilderForecast template - sample residential data included
Template purpose | Track proposed, submitted, approved and invoiced variations with cost, GST, time impact, approval references and ageing.
Sample project | Lot 14 Riverside Estate - New 4 Bedroom Residence
Project address | 14 Rivergum Circuit, NSW
Template pricing | TBC - pricing to be set after review
Best suited for | Residential builders, owner-builders, project managers and small construction teams
Positioning note | BuilderForecast supports project budget control, variations, allowances, subcontractor costs, cost-to-complete and reporting. MeasureBuild is the separate estimating and drawing review service.
Current BuilderForecast templates page | https://builderforecast.online/templates
BuilderForecast website | https://builderforecast.online
MeasureBuild website | https://measurebuild.com.au/
Workbook contents
1 | Dashboard
2 | Variation Register
3 | Client Summary
4 | Lists
How to use this template
1 | Update the contract value and status date on the Dashboard.
2 | Enter each variation in the Variation Register as soon as it is raised.
3 | Use Status to separate Draft, Submitted, Approved, Rejected and Invoiced items.
4 | Review the Client Summary before issuing a project budget update.
5 | Approved variations can be transferred into BuilderForecast to keep the current budget aligned with the real contract position.

## Lists (hidden)
Dropdown Lists
Editable lists used by dropdowns across this workbook.
Status | Raised By | Trade | Invoiced
Draft | Client | Preliminaries | No
Submitted | Builder | Concrete | Partly
Under Review | Architect | Framing | Yes
Approved | Engineer | Roofing
Rejected | Site Condition | Cladding
Invoiced | Authority | Windows
Closed |  | Plumbing
Electrical
Plasterboard
Tiling
Painting
Flooring
External Works

## Dashboard
Variation Register Dashboard
Variation cost control snapshot - approval status, client exposure and time impacts.
Project | Lot 14 Riverside Estate - New 4 Bedroom Residence | Original Contract Inc GST | 842000
Address | 14 Rivergum Circuit, NSW | Status Date | 2026-07-15
Project Manager | A. Project Manager | GST Rate | 10%
Approved Inc GST | 15675 | Status | Count
Submitted / Pending Inc GST | 17545 | Draft | 1
Rejected Inc GST | 0 | Submitted | 2
Total Time Impact Days | 0 | Under Review | 1
Open Variations | 4 | Approved | 2
Forecast Contract Inc GST | 857675 | Rejected | 0
|  | Invoiced | 0

## Variation Register
Variation Register
Track proposed, submitted and approved variations.
VO No | Date Raised | Raised By | Trade | Cost Code | Description | Reason / Trigger | Status | Submitted Ex GST | GST | Submitted Inc GST | Approved Inc GST | Time Impact Days | Approval Date | Client Ref | Invoiced? | Days Open | Notes
VO-001 | 2026-06-28 | Client | Windows | 08-100 | Upgrade aluminium windows to double glazed low-e units. | Client selection upgrade after contract. | Approved | 11800 | 1180 | 12980 | 12980 | 0 | 2026-07-07 | CI-004 | Yes | 9 | Approved before window order release.
VO-002 | 2026-07-02 | Site Condition | Concrete | 03-100 | Additional concrete pier depth due to soft spot at garage edge. | Unexpected site condition after excavation. | Submitted | 4850 | 485 | 5335 |  | 1 |  | RFI-SITE-012 | No | 13 | Awaiting client approval.
VO-003 | 2026-07-04 | Architect | Cladding | 07-200 | Change rear elevation cladding profile to vertical fibre cement. | Design change for facade articulation. | Under Review | 7200 | 720 | 7920 |  | 2 |  | SK-022 | No | 11 | Need supplier lead time confirmation.
VO-004 | 2026-07-05 | Builder | Roofing | 07-300 | Add roof access anchor points above plant deck. | Safety and maintenance requirement. | Draft | 1650 | 165 | 1815 |  | 0 |  |  | No | 10 | Drafting subcontractor quote.
VO-005 | 2026-07-08 | Client | Tiling | 09-300 | Upgrade ensuite wall tiles from standard range to feature tile. | Client selection upgrade. | Approved | 2450 | 245 | 2695 | 2695 | 0 | 2026-07-12 | CI-009 | No | 4 | Approved; invoice next claim.
VO-006 | 2026-07-09 | Engineer | Framing | 06-100 | Additional LVL beam over alfresco opening. | Engineering revision S04 Rev D. | Submitted | 3900 | 390 | 4290 |  | 1 |  | ENG-REV-D | No | 6 | Check flow-on to roofing install.

## Client Summary
Client Variation Summary
Client-facing summary of current variation position.
Project | Lot 14 Riverside Estate - New 4 Bedroom Residence
Prepared For | Client / Owner
Prepared By | Builder / PM
Status Date | 2026-07-15
Notes | Review before issue; confirm contract clauses and approval requirements.
VO No | Description | Status | Approved Inc GST | Submitted Inc GST | Time Impact Days
VO-001 | Upgrade aluminium windows to double glazed low-e units. | Approved | 12980 | 12980 | 0
VO-002 | Additional concrete pier depth due to soft spot at garage edge. | Submitted | 0 | 5335 | 1
VO-003 | Change rear elevation cladding profile to vertical fibre cement. | Under Review | 0 | 7920 | 2
VO-004 | Add roof access anchor points above plant deck. | Draft | 0 | 1815 | 0
VO-005 | Upgrade ensuite wall tiles from standard range to feature tile. | Approved | 2695 | 2695 | 0
VO-006 | Additional LVL beam over alfresco opening. | Submitted | 0 | 4290 | 1
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0
0 | 0 | 0 | 0 |  | 0